## Sheet1
Week | <component> | difficulty
2022-05-09 | Project Plan,Architechture plan | Easy
2022-05-16 | Coding environment and Source control setup | Medium
2022-05-23 | Build project | Medium
2022-05-30 | API Development | Difficult
2022-06-06 | FrontEnd Development | Medium
2022-06-13 | Integrate FrontEnd with API | Difficult
2022-06-20 | Ensure the APP runs Locally | Easy
2022-06-27 | Setup Azure Devops CI/CD Pipeline | Medium
2022-07-04 | Documentation | Easy
2022-07-11 | Ready for QA | Medium
2022-07-18
Goals
Logging
ML API Calls
CI/CD Pipeline
Q2 Plan | Build and Deploy project in Azure Cloud with CI/CD Pipeline
Yearly Plan | Run Regression testing Automated Suites for each upgrade to make sure systems working
Review code for coding standards